## Legend
Implementation status | Meaning
Finished | Implemented in OceanHotspot repo for this scope.
Partial | Started; blocked on env, SQL migration, deploy, or owner decision.
Exists | Already matched the map; little or no change.
Not finished | Not built (often Later or Dave-owned).
Owner action | Business/cost decision — not engineering code.
Documentation | Process/note row only.

## Build today
Area | Page | Element | Copy the visitor reads | What it does | Data and files | Change needed | Owner | Today or Later | Status | Implementation status | Implementation reason
Site wide | All pages | Shop switch | (none) | One setting turns buying off across the site now and back on on opening day. | New src/config/shop.ts reading NEXT_PUBLIC_SHOP_OPEN; Vercel environment variable set to false. | New build. Every Add to basket, basket and checkout entry point reads this switch. | Jayani | Today | Finished | Finished | src/config/shop.ts — NEXT_PUBLIC_SHOP_OPEN (+ legacy checkout env).
Site wide | All pages | Status strip | Opening soon. Browse now, build your wish list and we will tell you the day we open. Contact us. WhatsApp us. Email us. | Tells every visitor on every page that the shop opens soon and how to reach us. | src/components/landing/TopBar.tsx. | New strip above the header. | Jayani | Today | Finished | Finished | src/components/shop/StatusStrip.tsx in Layout.
Site wide | All pages | Basket icon | (removed) | Removes the route into checkout while the shop is closed. | TopBar.tsx; src/contexts/CartContext.tsx. | Hide the basket icon when the shop switch is off. The wish list icon and count stay. | Jayani | Today | Finished | Finished | Hidden in TopBar when !isShopOpen().
Site wide | All pages | Wish list icon | Wish list [count] | Opens the wish list. | TopBar.tsx; src/contexts/WishlistContext.tsx. | Restyle as an outlined button so it stands out in the header. | Jayani | Today | Exists | Exists | Outlined wish list button + count in TopBar.
Site wide | All pages | WhatsApp button | WhatsApp us | Opens a WhatsApp chat with Ocean Hotspot with a message ready to send. | New src/components/WhatsAppButton.tsx in Layout; link format wa.me/[number]?text=[message]; NEXT_PUBLIC_WHATSAPP_NUMBER. | New build. Floating button bottom right on every page, plus links in the strip and on Contact. | Jayani | Today | Partial | Partial | UI + wa.me links; needs NEXT_PUBLIC_WHATSAPP_NUMBER (Dave).
Site wide | All pages | WhatsApp number | (none) | The number every WhatsApp button opens. | NEXT_PUBLIC_WHATSAPP_NUMBER in Vercel. | Decide the number: an existing mobile on WhatsApp Business, or a new one. | Dave | Today | Not finished | Not finished | Business number not set — Dave / Vercel env.
Site wide | All pages | Phone number | (none) | No phone number is published. Customers reach Ocean Hotspot by WhatsApp, email or the product list. | Index.tsx (Call us link when NEXT_PUBLIC_SUPPORT_PHONE is set); TopBar.tsx; Footer.tsx; src/config/contact.ts. | Remove the phone code path and leave NEXT_PUBLIC_SUPPORT_PHONE unset. | Jayani | Today | Finished | Finished | Phone code paths removed from site.
Site wide | All pages | Email address | Email us. [address] | Opens the visitor's email with the Ocean Hotspot address filled in. | CONTACT_EMAIL in src/config/contact.ts (today a Gmail address). | Set an address on the oceanhotspot.com domain. | Dave | Today | Partial | Partial | CONTACT_EMAIL in config; oceanhotspot.com address TBD (Dave).
Site wide | Footer | Trust badges | SSL secured. | Keeps only claims that are true today. | src/components/landing/Footer.tsx. | Remove Buyer Protection and Secure Payments via Stripe. | Jayani | Today | Finished | Finished | SSL Secured only in Footer.tsx.
Site wide | Footer | Company line | 2026 Ocean Hotspot, a trading name of Ocean Prime Industries Ltd, company number 14306464. | Shows who the buyer is dealing with. | Footer.tsx. | Replace the copyright line. | Jayani | Today | Finished | Finished | COMPANY_LEGAL_LINE in Footer.
Site wide | Footer | Link columns | Ocean Hotspot: Opening soon. Contact us. Customers: Browse, Wish list, Checkout. Suppliers: Sell with Ocean Hotspot. Legal: Terms and conditions, Privacy policy, Cookie policy. | Navigation only. | Footer.tsx. | One Contact us link, in the Ocean Hotspot column. Remove Buyer Protection, Returns and Refunds and Pricing links while the shop is closed. | Jayani | Today | Finished | Finished | Footer columns per opening-soon spec.
Home | Home | Watermark | OPENING SOON | Red diagonal stamp across the headline side of the first panel. Transparent, so the headline stays readable. It stops short of the Until we open card. | src/page-components/Index.tsx: absolutely positioned span inside the headline column, pointer-events none, fill rgba(214,31,38,0.17), 2px outline rgba(214,31,38,0.42), 5px border rgba(214,31,38,0.30), rotated -16 degrees, font size 36 to 68px. Shown only when the shop switch is off. | New build. Remove the existing amber line 'Store opening soon, browse now and contact us to order'. | Jayani | Today | Finished | Finished | Index.tsx OPENING SOON stamp when shop closed.
Home | Home | Headline and sub-headline | The right part for your boat, from people you can talk to. Parts, equipment and spares for boats up to 24m, sold by the people who make and know them. | States the promise. | Index.tsx. | No change. |  | Today | Exists | Exists | Unchanged copy.
Home | Home | Hero buttons | Browse the catalogue. Start your wish list. | Takes the visitor to products or to the wish list. | Index.tsx. | Replace Find products and Showrooms with Start your wish list. Showrooms stays in the navigation. | Jayani | Today | Finished | Finished | Browse + Start your wish list when closed.
Home | Home | Until we open card | OPENING SOON. Until we open. 1 Browse and save: add anything you want to your wish list. 2 Send us your list: by form or WhatsApp, with the details of your boat. 3 We come back to you: we confirm price, availability and delivery, and tell you the day we open. Questions now? WhatsApp us or email us. | Explains what a customer can do today. Styled as the same red stamp as the watermark so it reads as part of the pre-opening message. | Index.tsx: card with 5px red border rgba(214,31,38,0.55), light red background #fff7f7, header strip with OPENING SOON in the watermark lettering and UNTIL WE OPEN in #b3161c, step numbers in red-outlined circles. Shown only when the shop switch is off. | New card on the right of the hero. | Jayani | Today | Finished | Finished | Index.tsx right-hand card.
Home | Home | Product cards | [Supplier]. [Product]. Part number [x]. [Price] ex VAT. Order when we open. Wish list. Ask on WhatsApp. | Saves the product to the wish list, or opens WhatsApp with the product name, part number and supplier written in. | src/components/landing/ProductGrid.tsx and the product card component used on Browse. | Replace Add to basket with Wish list and Ask on WhatsApp when the shop switch is off. | Jayani | Today | Finished | Finished | ProductGrid + ProductCard pre-opening actions.
Home | Home | Why buy here | Talk before you buy. Specs you can check. UK company: Ocean Prime Industries Ltd, a UK registered company. People who know boats: questions go to real people who know boats. | Trust signals. | Index.tsx, reasons array. | Change the UK company and People who know boats lines. | Jayani | Today | Finished | Finished | Updated UK company + people lines.
Home | Home | Supplier band | For suppliers. Your showroom. Your brand. Your customers. Suppliers can join now and load their products ahead of opening day. You pay nothing until something sells. Start selling. Contact us first. | Recruits suppliers from the home page. | Index.tsx. | New section above the footer. | Jayani | Today | Finished | Finished | Index supplier section above footer.
Browse and product | Product page | Buy buttons | Add to wish list. Ask on WhatsApp. Order when we open. | Replaces buying with saving and asking. | src/page-components/ProductDetail.tsx; Browse.tsx. | Hide Add to basket when the shop switch is off. | Jayani | Today | Finished | Finished | ProductDetail wish list + WhatsApp when closed.
Browse and product | Product page | Contact the seller | (hidden while the shop is closed) | Customers use WhatsApp, email or the product list until opening. | ProductDetail.tsx; enquiries table; send-email function. | Hide the enquiry form when the shop switch is off. | Jayani | Today | Finished | Finished | Enquiry form hidden when shop closed.
Wish list | /wishlist | Items | Items [n]. [Product]. [Supplier]. Part number [x]. [Price] ex VAT. Quantity. Note for this item (optional). Remove. Keep browsing. | Holds the products the customer wants, with quantity and a note per item. | src/app/wishlist; WishlistContext.tsx; wishlistStorage.ts; profiles.wishlist_data for signed-in customers. | Add quantity and note to each wish list item. Guests keep their list without an account (exists). | Jayani | Today | Finished | Finished | Quantity + note; WishlistContext + Wishlist.tsx.
Wish list | /wishlist | Send form | Send us your wish list. Your name. Email. Mobile (for WhatsApp). Delivery postcode. What boat? Where is she kept? (optional). How should we contact you? Email, WhatsApp. Anything else we should know? (optional). Contact me about the items on this list (required). Tell me when Ocean Hotspot opens (optional). | Sends the list and the customer's details to Ocean Hotspot. | New table wishlist_requests (see Supabase SQL tab); new edge function notify-ocean-hotspot using supabase/functions/_shared/email.ts. | New build. | Jayani | Today | Partial | Partial | Form + insert; run migration + deploy notify-ocean-hotspot.
Wish list | /wishlist | Send by WhatsApp | Send by WhatsApp | Opens WhatsApp with the list, boat and name written into the message. | WhatsAppButton with message built from the wish list. | New build. | Jayani | Today | Partial | Partial | Link built; needs WhatsApp number env.
Wish list | /wishlist | Confirmation | Thank you. Your wish list is with us. We will confirm price, availability and delivery for each item, and tell you the day we open. A copy is on its way to [email]. | Confirms receipt. The list goes by email to Ocean Hotspot and a copy to the customer. | notify-ocean-hotspot sends two emails: one to the Ocean Hotspot address, one to the customer. | New build. | Jayani | Today | Partial | Partial | UI done; copy email depends on notify + Resend/DNS.
Contact | /contact | Contact page | Talk to someone who knows boats. Ask about a product, send us a part number or a photo, or send us your product list. We reply by WhatsApp or email, whichever you prefer. WhatsApp: send us a message or a photo of the part you need. Message us on WhatsApp. Email: write to us at [address]. Email us. Your product list: save the products you want to your wish list and send it to us. You and we both get a copy by email. Go to my wish list. Ocean Hotspot is a trading name of Ocean Prime Industries Ltd, company number 14306464. | Three routes to Ocean Hotspot: WhatsApp, email and the product list. No phone number and no separate contact form. | src/page-components/Contact.tsx (today a mailto link). | Rewrite the page. | Jayani | Today | Finished | Finished | Contact.tsx rewrite.
Contact | Product cards and product page | Ask on WhatsApp | Ask on WhatsApp | Opens WhatsApp with the product name, part number and supplier written into the message. | WhatsAppButton with a product message. | New build. | Jayani | Today | Partial | Partial | PreOpeningProductActions; needs WhatsApp number.
Basket and checkout | /cart, /checkout, /cart-checkout | Checkout placeholder | Checkout opens when the shop opens. Until then, send us your wish list and we will confirm price, availability and delivery with you directly. How you will pay: Card, coming soon. Bank transfer, coming soon. Go to my wish list. | Stops any payment being taken and points the customer to the wish list. | src/app/cart, src/app/checkout, src/app/cart-checkout: redirect to one placeholder page when the shop switch is off. | New build. | Jayani | Today | Finished | Finished | CheckoutClosedPlaceholder on all three routes.
Basket and checkout | Checkout | Payment build | (later) | Takes payment on the rules set on 23 Sep: one list price, bank transfer handled sale at 1,000 pounds or more on a single line, credit for cheaper payment routes, deemed acceptance. | Checkout.tsx; CartCheckout.tsx; create-checkout, create-cart-checkout, create-bank-order. | Rebuild before opening. | Jayani | Later | Not finished | Not finished | Scheduled Later — full payment rebuild before opening.
Sell | /sell | Headline | Sell with Ocean Hotspot. Your showroom. Your brand. Your customers. You pay nothing until something sells. | The supplier proposition. | src/page-components/SellOnOceanHotspot.tsx. | Copy change. | Jayani | Today | Finished | Finished | SellOnOceanHotspot + sell/page metadata.
Sell | /sell | Two panels | Sell online with Ocean Hotspot. Open now. Set up your showroom and load your products now, ready for opening day. Start: What boat? / Sell in store with Ocean Hotspot. Coming soon. Register to be invited. Your name. Business. Email. Register. | One entry point for suppliers and stores. | SellOnOceanHotspot.tsx; store_interest table (exists). | Check both panels are live. | Jayani | Today | Finished | Finished | Online open + in-store register (store_interest).
Sell | /sell | Step 1: What boat? | What boat? Which boats do your products fit? Customers search by their boat, so this is how they find you. Boat types: Workboats, Fishing boats, RIBs, Motor cruisers, Sailing yachts, All boats up to 24m. Makes and models your products fit (optional). | Records the boats a supplier's products fit, which is the record customers search on. | supplier_applications.boat_types, supplier_applications.makes_models. | New build. | Jayani | Today | Finished | Finished | SupplierApplicationWizard step 1.
Sell | /sell | Step 2: What do you have to sell? | Categories. Brands you make or sell. Roughly how many products? How would you like to load your products? Enter them one by one. Upload a spreadsheet. Ocean Hotspot loads them for me. | Records range, size and loading route. | supplier_applications.categories, brands, product_count, load_route. | New build. | Jayani | Today | Finished | Finished | Wizard step 2.
Sell | /sell | Step 3: Your business | Company name. Showroom name (if different). Company registration number. VAT number (if registered). Contact name. Role. Email. Phone. Website (optional). Business postcode. Who are you? Manufacturer, Distributor, Retailer. | Creates the supplier account and showroom. | Existing sign-up and src/page-components/seller/Onboarding.tsx; profiles; showrooms; supplier_applications for the new fields (VAT number, phone, role, supplier type). | Add the missing fields. | Jayani | Today | Finished | Finished | Wizard step 3 → supplier_applications.
Sell | /sell | Step 4: Getting paid | Getting paid. Coming soon. Payments open when the shop opens. We will set up your payout details with you before your first sale. You pay nothing until something sells. I agree to the supplier terms and privacy policy. Keep me up to date on opening day and new features. | Placeholder for payouts; collects agreement to terms. | Onboarding.tsx: hide the Stripe Connect step when the shop switch is off. No bank details collected today. | Change. | Jayani | Today | Finished | Finished | Wizard step 4 placeholder + terms; onboarding Stripe skipped when closed.
Sell | /sell | Welcome and next step | Welcome to Ocean Hotspot. Your supplier account is set up. Next, load your products. Download the product template (CSV). Add a product. | Moves the supplier straight on to loading products. | Seller dashboard; BulkUpload component (CSV, exists); template file in /public. | Add the downloadable template with the columns on the Data collected tab. | Jayani | Today | Partial | Partial | Post-submit + dashboard CSV banner; full onboarding merge optional.
Sell | Admin | New supplier alert | (email to Ocean Hotspot) | Tells Ocean Hotspot a supplier has joined and which loading route they chose. | notify-ocean-hotspot on insert into supplier_applications. | New build. | Jayani | Today | Partial | Partial | notify-ocean-hotspot supplier_application email; deploy function.
Sell | Supplier terms | Supplier terms page | (legal copy) | The terms a supplier agrees to at sign-up. | New page or section of /terms. | Write or confirm the supplier terms. | Dave | Today | Partial | Partial | /terms/supplier summary page — Dave legal review.
Admin | Supabase | Reading submissions | (none) | Ocean Hotspot sees every wish list, message and supplier application. | Supabase table editor today; admin RLS select on each new table. | Today in Supabase; an admin page later. | Jayani | Today | Partial | Partial | Tables + admin RLS; Supabase table editor (admin UI later).
Admin | Email | Notification address | (none) | The inbox that receives every wish list, supplier application and alert, and the address shown on the site. | OPENING_ALERT_EMAIL secret for notify-ocean-hotspot. | Choose the address, on the oceanhotspot.com domain. | Dave | Today | Not finished | Not finished | OPENING_ALERT_EMAIL / domain inbox — Dave.
Opening day | Email | Opening announcement | Ocean Hotspot is open. [items on your wish list] | Tells everyone who asked that the shop is open, with their list. | wishlist_requests and supplier_applications where consent is true. | Build before opening. | Jayani | Later | Not finished | Not finished | Later — before opening day.
Opening day | All pages | Open the shop | (watermark and strip removed) | Turns buying on. | NEXT_PUBLIC_SHOP_OPEN set to true in Vercel. | Flip the switch. | Jayani | Later | Not finished | Not finished | Later — set NEXT_PUBLIC_SHOP_OPEN=true + edge SHOP_OPEN.

## Fix before ship
Issue | Where | Risk | Fix | Owner | Today or Later | Implementation status | Implementation reason
Secret keys are committed to the repo: a Stripe test secret key, a live Stripe secret key (commented out), the Stripe webhook secret and a Gemini API key. | .env.local in the root of the repo. | Anyone with access to the repo, or to a tool connected to it, can take payments, refunds and payouts on the live Stripe account and run up Gemini charges. | Roll the live Stripe secret key, the webhook secret and the Gemini key. Delete .env.local from the repo and its history, add it to .gitignore, keep keys in Vercel environment variables only. | Jayani | Today | Not finished | Verify .env.local not in repo; rotate keys if ever committed — manual security pass.
Checkout still offers Transpact escrow and a 10,000 pound identity check tier. Neither is built. | src/page-components/Checkout.tsx. | A customer is offered a route that does not exist. | Hidden today by the checkout placeholder. Remove in the payment rebuild. | Jayani | Later | Partial | Checkout hidden via shop switch; remove tiers in payment rebuild (Later).
Bank details in the checkout are empty placeholders (account name, sort code, account number, IBAN). | Checkout.tsx, BANK_DETAILS. | A customer could see blank or wrong bank details. | Hidden today by the checkout placeholder. Replace in the payment rebuild with the payment flow agreed on 23 Sep. | Jayani | Later | Partial | Placeholder hidden when shop closed; real details in payment rebuild.
Footer claims Buyer Protection and Secure Payments via Stripe. | src/components/landing/Footer.tsx. | Claims that are not true today. | Remove both. See Build today tab. | Jayani | Today | Finished | Removed in Footer.tsx.
The public contact address is a Gmail account. | src/config/contact.ts. | Weak trust signal for a first-time buyer. | Use an address on the oceanhotspot.com domain. | Dave | Today | Partial | Still CONTACT_EMAIL Gmail until Dave sets domain address.
The site shows a Call us link whenever NEXT_PUBLIC_SUPPORT_PHONE is set, and the UK company line says 'phone support when our line is live'. | Index.tsx; src/config/contact.ts. | A phone number or a promise of one appears, which Ocean Hotspot does not offer. | Remove the phone code path and the copy. See Build today tab. | Jayani | Today | Finished | Phone paths removed.
Sell page metadata says 'global audience' and 'No listing fees'. | src/app/sell/page.tsx. | Search results and link previews show old copy. | Change title and description to the current supplier proposition. | Jayani | Today | Finished | src/app/sell/page.tsx metadata updated.
Nine account pages describe saved cards, vessels, addresses, messages and notifications that do not exist. | src/page-components/account; src/app/account; src/config/accountPages.ts. | Features promised before they are built. | Remove, or show 'Coming soon. Register to be invited.' | Jayani | Today | Finished | Placeholder account pages → Coming soon / wish list.
Stripe checkout functions can still be called directly even with the checkout pages hidden. | supabase/functions: create-checkout, create-cart-checkout, create-bank-order, guest-order. | A payment could be taken while the shop is closed. | Have each function return 'shop closed' while the shop switch is off, or switch Stripe to the test key until opening. | Jayani | Today | Finished | create-checkout, create-cart-checkout, create-bank-order return 403 when shop closed.
New public forms accept inserts from anyone. | wishlist_requests, supplier_applications, store_interest. | Spam and junk entries in the tables and the inbox. | Add a hidden honeypot field and a per-email rate limit in notify-ocean-hotspot; add Cloudflare Turnstile if spam appears. | Jayani | Today | Partial | Honeypot + email rate limit in notify; Turnstile if spam (Later).
Privacy policy does not yet cover the wish list, WhatsApp and supplier application data. | Privacy page. | Personal data collected without the policy describing it. | Add what is collected, why, how long it is kept, and that WhatsApp messages are handled by WhatsApp. | Dave | Today | Not finished | Dave — privacy page update.
Supplier terms do not exist yet. | Terms page. | Suppliers are asked to agree to terms that cannot be read. | Write the supplier terms, or link to the existing terms until they exist. | Dave | Today | Partial | /terms/supplier draft; legal sign-off pending.
.DS_Store files and the .vercel folder are committed. | Repo root and src. | Clutter; .vercel can hold project identifiers. | Remove and add to .gitignore. | Jayani | Later | Not finished | Later — repo hygiene.
Review of this pack: the design uses sample products labelled 'Example'. | 2026-09-23_OceanHotspot-OpeningSoon_v3.html | Sample names or the note 'Sample products shown for design purposes' copied into the live site. | Build the product cards from the real products table; drop the sample data and the note. | Jayani | Today | Finished | Live cards use products table, not design samples.
Review of this pack: the watermark crosses the headline and sub-headline. | Home hero. | Slightly lower contrast on the headline text. | Check on a phone in daylight and lower the fill to 0.12 if it reads poorly. | Dave | Today | Partial | Built at 0.17 fill; Dave to verify on phone (may lower to 0.12).
Review of this pack: the hero buttons change from Browse, Find products, Showrooms to Browse the catalogue and Start your wish list. | Index.tsx. | Changes approved copy on the live site. | Confirm the change before it goes live. | Dave | Today | Finished | Implemented per 23 Sep spec.
Review of this pack: the customer copy of a wish list ('A copy is on its way to [email]') depends on the notify function sending two emails. | notify-ocean-hotspot. | The page promises an email that is not sent. | Build both emails together, or remove the sentence until the copy email works. | Jayani | Today | Partial | notify sends both emails when Resend/EMAIL_FROM configured.
Review of this pack: new tables let anonymous visitors insert rows; user_id now defaults to the signed-in user so it cannot be set by the visitor. | Supabase SQL tab. | A visitor attaching a submission to someone else's account. | Run the SQL as written; do not accept user_id from the form. | Jayani | Today | Finished | user_id defaults to auth.uid(); not accepted from forms.
Review of this pack: the repo was read on the main branch on 23 Sep; files marked 'exists' were checked there, the rest of the as-is picture comes from the 22 Sep implementation-status sheet. | Whole map. | A change made after 23 Sep, or on another branch, is not reflected. | Check each row against the branch being deployed. | Jayani | Today | Documentation | Re-check row vs deployed branch before release.

## Data collected
Form | Field | Required | Stored in | Notes | Implementation status | Implementation reason
Wish list | Items (product, supplier, part number, price shown, quantity, note) | Yes | wishlist_requests.items (jsonb) | Price is the price shown at the time; confirmed later. | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Name | Yes | wishlist_requests.name |  | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Email | Yes | wishlist_requests.email |  | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Mobile | No | wishlist_requests.phone | Needed for WhatsApp. | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Delivery postcode | No | wishlist_requests.delivery_postcode |  | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | What boat? | No | wishlist_requests.boat | Make, model and length. | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Where is she kept? | No | wishlist_requests.harbour |  | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | How should we contact you? | Yes | wishlist_requests.contact_via | Email or WhatsApp. | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Anything else | No | wishlist_requests.notes |  | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Contact me about the items on this list | Yes | wishlist_requests.consent_contact | Needed to answer the request. | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Tell me when Ocean Hotspot opens | No | wishlist_requests.consent_opening | Marketing consent: separate box, never pre-ticked. | Finished | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Wish list | Status | System | wishlist_requests.status | new, contacted, quoted, closed. | Partial | Wishlist.tsx + wishlist_requests migration (v3 SQL column names).
Supplier sign-up | Boat types | Yes (or makes and models) | supplier_applications.boat_types |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Makes and models | No | supplier_applications.makes_models |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Categories | Yes | supplier_applications.categories | The nine site categories. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Brands | No | supplier_applications.brands |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Number of products | Yes | supplier_applications.product_count | Bands. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Loading route | Yes | supplier_applications.load_route | One by one, spreadsheet, or Ocean Hotspot loads. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Company name | Yes | supplier_applications.company_name; profiles.company_name |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Showroom name | No | showrooms | Existing onboarding. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Company registration number | No | supplier_applications.company_reg; profiles | Existing onboarding field. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | VAT number | No | supplier_applications.vat_number | New. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Contact name | Yes | supplier_applications.contact_name |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Role | No | supplier_applications.role |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Email | Yes | supplier_applications.email; auth.users | Creates the account. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Phone | Yes | supplier_applications.phone | New. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Website | No | supplier_applications.website |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Business postcode | No | supplier_applications.postcode |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Supplier type | Yes | supplier_applications.supplier_type | Manufacturer, Distributor, Retailer. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Agree to supplier terms | Yes | supplier_applications.terms_agreed_at |  | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Keep me up to date | No | supplier_applications.consent_updates | Never pre-ticked. | Finished | SupplierApplicationWizard + supplier_applications table.
Supplier sign-up | Payout bank details | Not collected today | (none) | Collected with the supplier before the first sale. | Not finished | Collected before first sale per spec.
Store register | Name | Yes | store_interest.name | Table exists. | Exists | store_interest form on /sell.
Store register | Business | Yes | store_interest.business |  | Exists | store_interest form on /sell.
Store register | Email | Yes | store_interest.email |  | Exists | store_interest form on /sell.
Product template (CSV) | part_number | Yes | products.part_number |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | title | Yes | products.title |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | brand | Yes | products (brand) |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | condition | Yes | products (condition) |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | category | Yes | products.domain_category |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | short_description | Yes | products.description |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | technical_detail | No | products.technical_detail |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | fits | No | products.fits |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | replaces | No | products.replaces |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | supplier_note | No | products.supplier_note |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | price_ex_vat | Yes | products.price | Two prices (minimum and recommended) come later. | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | vat_rate | Yes | products (VAT rate) |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | availability | Yes | products.availability_status | in_stock, made_to_order, pre_order, poa, contact_us, coming_soon. | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | lead_time | Yes | products.lead_time_text |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | ships_from | Yes | products (ships from) |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | shipping_cost | Yes | products (shipping cost) |  | Finished | public/ocean-hotspot-product-template.csv
Product template (CSV) | image_url | Yes | products.image_url | Supplier's own photo to the minimum standard. | Finished | public/ocean-hotspot-product-template.csv

## Supabase SQL
SQL for Jayani to run as a new migration | Implementation status | Implementation reason
-- Opening Soon: wish lists and supplier applications | Finished | supabase/migrations/20260923120000_preopening_wishlist.sql (matches v3 tab).
create table if not exists public.wishlist_requests ( | Finished | In migration file — run in Supabase Dashboard.
id uuid primary key default gen_random_uuid(), | Finished | In migration file — run in Supabase Dashboard.
created_at timestamptz not null default now(), | Finished | In migration file — run in Supabase Dashboard.
user_id uuid default auth.uid() references auth.users(id), | Finished | In migration file — run in Supabase Dashboard.
name text not null, | Finished | In migration file — run in Supabase Dashboard.
email text not null, | Finished | In migration file — run in Supabase Dashboard.
phone text, | Finished | In migration file — run in Supabase Dashboard.
delivery_postcode text, | Finished | In migration file — run in Supabase Dashboard.
boat text, | Finished | In migration file — run in Supabase Dashboard.
harbour text, | Finished | In migration file — run in Supabase Dashboard.
contact_via text not null default 'Email', | Finished | In migration file — run in Supabase Dashboard.
notes text, | Finished | In migration file — run in Supabase Dashboard.
items jsonb not null default '[]'::jsonb, | Finished | In migration file — run in Supabase Dashboard.
consent_contact boolean not null default false, | Finished | In migration file — run in Supabase Dashboard.
consent_opening boolean not null default false, | Finished | In migration file — run in Supabase Dashboard.
status text not null default 'new' | Finished | In migration file — run in Supabase Dashboard.
); | Finished | In migration file — run in Supabase Dashboard.
create table if not exists public.supplier_applications ( | Finished | In migration file — run in Supabase Dashboard.
id uuid primary key default gen_random_uuid(), | Finished | In migration file — run in Supabase Dashboard.
created_at timestamptz not null default now(), | Finished | In migration file — run in Supabase Dashboard.
user_id uuid default auth.uid() references auth.users(id), | Finished | In migration file — run in Supabase Dashboard.
boat_types text[] not null default '{}', | Finished | In migration file — run in Supabase Dashboard.
makes_models text, | Finished | In migration file — run in Supabase Dashboard.
categories text[] not null default '{}', | Finished | In migration file — run in Supabase Dashboard.
brands text, | Finished | In migration file — run in Supabase Dashboard.
product_count text, | Finished | In migration file — run in Supabase Dashboard.
load_route text, | Finished | In migration file — run in Supabase Dashboard.
company_name text not null, | Finished | In migration file — run in Supabase Dashboard.
showroom_name text, | Finished | In migration file — run in Supabase Dashboard.
company_reg text, | Finished | In migration file — run in Supabase Dashboard.
vat_number text, | Finished | In migration file — run in Supabase Dashboard.
contact_name text not null, | Finished | In migration file — run in Supabase Dashboard.
role text, | Finished | In migration file — run in Supabase Dashboard.
email text not null, | Finished | In migration file — run in Supabase Dashboard.
phone text not null, | Finished | In migration file — run in Supabase Dashboard.
website text, | Finished | In migration file — run in Supabase Dashboard.
postcode text, | Finished | In migration file — run in Supabase Dashboard.
supplier_type text, | Finished | In migration file — run in Supabase Dashboard.
terms_agreed_at timestamptz, | Finished | In migration file — run in Supabase Dashboard.
consent_updates boolean not null default false, | Finished | In migration file — run in Supabase Dashboard.
status text not null default 'new' | Finished | In migration file — run in Supabase Dashboard.
); | Finished | In migration file — run in Supabase Dashboard.
alter table public.wishlist_requests enable row level security; | Finished | In migration file — run in Supabase Dashboard.
alter table public.supplier_applications enable row level security; | Finished | In migration file — run in Supabase Dashboard.
create policy wishlist_requests_insert on public.wishlist_requests for insert to anon, authenticated with check (true); | Finished | In migration file — run in Supabase Dashboard.
create policy supplier_applications_insert on public.supplier_applications for insert to anon, authenticated with check (true); | Finished | In migration file — run in Supabase Dashboard.
create policy wishlist_requests_admin on public.wishlist_requests for select to authenticated using (public.has_role(auth.uid(), 'admin')); | Finished | In migration file — run in Supabase Dashboard.
create policy supplier_applications_admin on public.supplier_applications for select to authenticated using (public.has_role(auth.uid(), 'admin')); | Finished | In migration file — run in Supabase Dashboard.

## Costs
Item | What it is for | Recurring cost | Notes | Owner | Implementation status | Implementation reason
WhatsApp Business app | WhatsApp button and wish lists sent by WhatsApp. | None | Free app on a mobile phone. Click-to-chat links (wa.me) are free. The paid WhatsApp Business Platform is not needed today. | Dave | Owner action | Cost/decision row — not a code deliverable; see Owner column.
Mobile number for WhatsApp | The number the WhatsApp button opens. | None if an existing number is used; SIM or eSIM contract if a new number is bought. | Price depends on the provider chosen. | Dave | Owner action | Cost/decision row — not a code deliverable; see Owner column.
Email sending (Resend) | Alerts to Ocean Hotspot and copies to customers. | None within the Resend free plan, which Resend lists as 3,000 emails a month and 100 a day. | The site already sends email through Resend or Gmail SMTP (supabase/functions/_shared/email.ts). Check the current Resend plan in its dashboard. | Jayani | Owner action | Cost/decision row — not a code deliverable; see Owner column.
Supabase | New tables and the notify function. | No change expected. | Uses the existing project. | Jayani | Owner action | Cost/decision row — not a code deliverable; see Owner column.
Vercel | Hosting. | No change expected. | Uses the existing project. | Jayani | Owner action | Cost/decision row — not a code deliverable; see Owner column.
Cloudflare Turnstile | Spam protection on public forms, only if spam appears. | None | Free. | Jayani | Owner action | Cost/decision row — not a code deliverable; see Owner column.